MEETING SUMMARY

Northstar Studio · Delivery check-in

12 September 2026  |  Fictional demonstration data

# Executive summary

The team is preparing for a 30 September 2026 launch. Work is focused on the landing page, supplier confirmation, and packaging. The initial release will remain limited to three products. Packaging is now assigned to Theo and is due 20 September 2026.

# Key dates

16 September 2026 — Theo to confirm supplier availability; availability is not yet confirmed.

18 September 2026 — Maya to complete the landing page draft.

30 September 2026 — Planned launch date.

# Decisions

Keep the initial release to three products.

Approve a maximum materials budget of EUR 2,500.00. This is a budget ceiling, not recorded spending.

# Open question

Supplier availability is not yet confirmed; Theo is due to confirm it by 16 September 2026.

# What changed

Follow-up update: packaging changed from unassigned with no deadline to Theo as owner, due 20 September 2026. No other decisions or dates were changed.

# Actions

| Owner | Action | Due date |
| --- | --- | --- |
| Maya | Prepare the landing page draft | 18 September 2026 |
| Theo | Confirm supplier availability | 16 September 2026 |
| Theo | Resolve packaging | 20 September 2026 |

# Invoice snapshot

| Measure | Amount |
| --- | --- |
| Total invoiced | EUR 1,850.00 |
| Paid | EUR 785.50 |
| Unpaid | EUR 1,064.50 |
| Materials invoices | EUR 855.50 |

Note: Invoice figures are reconciled from the accompanying export. This document preparation is not financial advice.